## Cronograma de projeto
Python Reports Project
COMPANY NAME |  | ICM COMPUTER | [5 empty] | ENGINEER |  |  |  |  | HOURS | [7 empty] | PHASE |  |  | HOURS
DATA |  | 2024-10-25 | [5 empty] | Nicolas |  |  |  |  | 7 |  |  | 100% |  | Nicolas | 7 |  | Phase 1 |  |  | 7 |  |  |  |  | 100% |  | Phase 1 | 7 | 0
PROJECT NAME |  | PYTHON REPORTS | [5 empty] | Darren |  |  |  |  | 0 |  |  | 0% |  | Darren | 0 |  | Phase 2 |  |  | 0 |  |  |  |  | 0% |  | Phase 2 | 0 | 0
PROJECT REF |  | 80002 | [5 empty] | Derek |  |  |  |  | 0 |  |  | 0% |  | Derek | 0 |  | Phase 3 |  |  | 0 |  |  |  |  | 0% |  | Phase 3 | 0 | 0
PROJECT LEADER |  | Pearse | [5 empty] | Paul H |  |  |  |  | 0 |  |  | 0% |  | Paul H | 0 |  | Phase 4 |  |  | 0 |  |  |  |  | 0% |  | Phase 4 | 0 | 0
TOTAL HOURS |  | 7 | [5 empty] | Steve |  |  |  |  | 0 |  |  | 0% |  | Steve | 0 |  | Phase 5 |  |  | 0 |  |  |  |  | 0% |  | Phase 5 | 0 | 0
START DATE |  | 2024-10-25 | [5 empty] | TOTAL |  |  |  |  | 7 |  |  |  |  | TOTAL | 7 |  | Phase 6 |  |  | 0 |  |  |  |  | 0% |  | Phase 6 | 0 | 0
TARGET DATE |  | 2024-11-28 | [18 empty] | TOTAL |  |  | 7
 | time axis 2024-10-25 to 2024-12-21
[8 empty] | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec
[8 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
PHASE | GOAL |  |  | TASKS | Engineer | Hours | Days | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Target start date: |  | 2024-10-25
1 | First Live test |  | 1 | Include Date Parameters ( Date, Time, Defaults [YTD,Quarter,Week,Month,Last 30 Days] | Nicolas | 7
2
| Develop a prototype featuring key reports, interactive widgets, and dynamic visualizations. The goal is to validate functionality and the visual interface, ensuring they surpass SSRS limitations. |  | 3
4
5
6
7
8
9
10
11
12
| Phase 1 |  |  |  | Total | 7
Target start date:
2 | Review and Feedback Phase
Collect feedback on the prototype, adjust functionalities and interface based on received comments and revisions.
| Phase 2 |  |  |  | Total | 0
Target start date:
3 | Template Creation and Testing |  | 1
2
| Develop templates for future reports to standardize visuals and interactions, prepare an on-premises installation package for local use, and estimate the time needed to create new reports from Python templates compared to generating current SSRS reports. |  | 3
3
4
4
4
| Phase 3 |  |  |  | Total | 0
Target start date:
4 | Versioning control |  | 1
1
| Implement version control for the project in Azure DevOps to enable efficient project management, code deployment, and version tracking. |  | 1
2
2
2
| Phase 4 |  |  |  | Total | 0
Target start date:
5 | Testing and Quality Assurance (QA) |  | 1
2
| Conduct extensive testing to ensure system reliability and performance. This phase includes integration, performance, and user acceptance testing |  | 2
2
2
5
| Phase 5 |  |  |  | Total | 0
Target start date:
6 | Monitoring and Logging |  | 1
1
| Set up monitoring and logging mechanisms to track errors, performance metrics, and user activity after deployment |  | 1
2
2
2
| Phase 6 |  |  |  | Total | 0
Note on C18: Nicolas Da Silva: 1. Initial Demo Phase Description: Develop a prototype featuring key reports, interactive widgets, and dynamic visualizations. The goal is to validate functionality and the visual interface, ensuring they surpass SSRS limitations. Deliverables: - Functional prototype with dynamic and interactive reports. - Charts and tables based on data extracted through existing stored procedures. - Simplified interface with optimized navigation.
Note on G33: Nicolas Da Silva: Collect feedback on the prototype, adjust functionalities and interface based on received comments and revisions

## Sheet1
Engineer
Nicolas
Darren
Derek
Paul H
Steve
Pearse